## Sheet1
| Task | Priority | Duration | Dependencies
| ---------- | -------------- | -------------- | --------------
1 | Collect Data on Existing Solutions and Plugins | High | 3 weeks | None
2 | Decide on Data Structure and Model Integration | High | 4 weeks | Task1
3 | Design and Create a Prototype | High | 5 weeks | Task2
4 | Prepare Code Snippets and Large Codebases | Medium | 3 weeks | None, but should be done before Task 5
5 | Test the Model Using Prepared Code Snippets | High | 4 weeks | Task3,Task4
6 | Evaluate the Model’s Performance | High | 2 weeks | Task5
7 | Implement Federated Learning Script | High | 4 weeks | Task6
8 | Aggregate and Evaluate Models | High | 5 weeks | Task7
9 | Iterate and Improve the Model | Medium | 7 weeks | Task8
10 | Integrate the Model into the IDE | Low | 4 weeks | Task9